## Taul1
UCD 2020 - Group project schedule | Deadline - Task | RED = 0% complete, YELLOW = 50% complete, GREEN = 100% complete.
Assigned person | Week 1 - Topic selection and starting the blog | Week 2 - Data preparation | Week 3 - Data collection | Week 4 - Data analysis and interpretation | Week 5 - Prototyping | Week 6 - Final report
Tony Heikkilä - Manager | Create a blog / Attend the group meeting | Group meeting and Google Forms creation | Find at least 2 participants to the survey. | Make a summary of the survey data on the blog | Test prototypes with two users and create a meeting for the presentation | Paper: Overall structure and conclusions
Jukka Arponen - Data capture | Attend the group meeting | Group meeting and Google Forms creation | Find at least 2 participants to the survey. | Create two personas based on the survey participant data | Presentation: Introduction + Epic Games Store | Paper: Introduction
Antti Auvinen - Designer | Attend the group meeting | Group meeting and Google Forms creation | Find at least 2 participants to the survey. | Start designing early prototypes | Additional prototypes, mockups and features | Paper: Prototyping
Matti Auvinen - Data capture and testing | Attend the group meeting | Group meeting and Google Forms creation | Find at least 2 participants to the survey. | Start designing early prototypes | Design possible testable things with users. Additional prototype designs. | Paper: Protyping and testing
Juhana Ullgren - Analyst | Attend the group meeting | Group meeting and Google Forms creation | Find at least 2 participants to the survey. | Write actionable recommendations about the data | Initial text in the final report, data analysis for the presentation. | Paper: Data analysis and actionable recommendations
Comments | Group topic was discussed and selected. The blog was created by Tony in GitHub. | Google Forms was selected as a data collection platform. Questions for the questionnaire were selected in a group meeting. | Form was shared to other CS students and their friends. We received 11 participants in total. | The task assignments were split between each group member. Meeting was held on the weekend after most of the tasks were done. | Presentation was held before the video presentation. Everyone participated in the presentation and final report segments were assigned. | Paper and blog completed, no additional meeting was needed after the presentation.